**Project Title : News Hunter**

**Roadmap**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No** | **Module Name** | **Owner** | **Start Date** | | **Completion Date** | | **Status** |
| **Planned** | **Actual** | **Planned** | **Actual** |
| 1 | Project Initialization on GitHub and adding collaborators | Repo owner : Priyavardhan  Collaborators: Aastha, Mauneel | 23/1/2021 | 15/1/2021 | 30/1/2021 | 28/1/2021 | Done |
| 2 | Web Scraping news and store in Database | Priyavardhan | 27/1/2021 | 27/1/2021 | 13/2/2021 | 3/2/2021 | Done |
| 3 | Displaying news on webpage | Priyavardhan | 27/1/2021 | 2/2/2021 | 13/2/2021 | 4/2/2021 | Done |
| 4 | Updating news | Priyavardhan | 27/1/2021 | 2/2/2021 | 13/2/2021 | 4/2/2021 | Done |
| 5 | Deleting old news | Priyavardhan | 27/1/2021 | 11/2/2021 | 13/2/2021 | 12/2/2021 | Done |
| 6 | Show weather report | Priyavardhan | 13/2/2021 | 18/2/2021 | 20/2/2021 | 18/2/2021 | Done |
| 7 | Populating Category webpages | Priyavardhan | 13/2/2021 | 14/2/2021 |  |  | In progress |
| 8 | Developing classification model to divide news into categories | Aastha | 23/12/2020 | 26/12/2020 | 26/1/2021 | 10/2/2021 | Done |
| 9 | Integrating the classification model into the web application | Aastha | 16/2/2021 | 18/2/2021 |  |  | In progress |
| 10 | User Interface, Logo Design and Favicon design | Mauneel | 22/1/2021 | 20/1/2021 | 23/1/2021 | 23/1/2021 | Done |
| 11 | Admin Module | Mauneel | 27/1/2021 | 22/1/2021 | 31/1/2021 | 30/1/2021 | Done |
| 12 | Push Notifications | Mauneel | 8/2/2021 | 8/2/2021 | 13/2/2021 | 13/2/2021 | Done |
| 13 | Search Functionality | Mauneel | 15/2/2021 | 16/2/2021 |  |  | In Progress |